## Change Process
CCS O&M · Change Management Process Flow / 変更プロセスフロー
|  | User |  |  | Call Center | CCS O&M Team |  |  | Other OPER Team | IB1 / Related
No. | Sub-Process | Vehicle Owner (end user) | Region CCS (ZNTC/NTC) | Plant (DCM System) | Call Center (NML Region) | L2 (LY) | L3 (LY) | Service Manager (LY) | Other OPER (ZNTC/DNTC/MNO) | IB1 / System Owner | Related Process
0 | Change Intake | Authorization |  |  | L1 (NML Region) | Prod Data Access Request
1 | [9 empty] | Incident Mgmt Process | Problem Mgmt Process
2 | [5 empty] | Create Change Ticket (Log details / confirm source Link incident/problem ID)
3 | [5 empty] | ◆ Initial Impact Assessment (Low / Mid / High per Change Matrix) |  | Impact Review (Service Manager / Region) |  | Mid / High → Region Final Confirmation
4 |  | ◆ Change Confirmation (No → Reject & Redesign) |  |  |  | Region finalizes Mid/High → assign to L2 |  |  |  | ⚠ Need Confirm with IB1
5 | [6 empty] | Assign to L3 (by change type)
6 | Change Resolution | [5 empty] | ◆ Collaboration Needed? (with external supporting team)
7 | [6 empty] | Collaborative Countermeasure (Coordination plan & countermeasures per problem & requirements) |  | Collaborative Countermeasure (Other OPER Team)
8 | [6 empty] | Develop Temporary Solution (Create the solution) |  | Develop Temporary Solution (Other OPER Team)
9 | [6 empty] | Change Plan Design (Define: Team / Tasks / Method / Schedule per Change Plan Template)
10 | [6 empty] | ◆ Plan Verification (Preliminary validation) No → Redesign ↑
11 | [6 empty] | Impact Classification (Preliminary impact rating → submit to Service Manager) | Review & Approve (Assess plan based on validation)
12 | [7 empty] | Impact Review Result ■ High → Region approval ■ Mid → Plan Manager decides
13 |  | ◆ Change Confirm (Region final rating) No → Reject, Redesign ↑ | [7 empty] | Final Confirmation
14 | Change Closure | [5 empty] | Change Implementation (Accept ticket in ops platform Snapshot all config items)
15 | [6 empty] | ◆ Release Success Check (Verify post-implementation Implementer confirms per plan) No → Rollback ↓
16 | [6 empty] | ⚠ Execute Rollback Plan (if change fails) Per change plan | Rollback Plan Review
17 | [6 empty] | ✓ Change Completed Close Change Ticket (if successful → update details) | Confirm Change Completion (Service Manager confirms then closes ticket)
18 |  | Change Result Report |  |  |  |  | Email Notification (Notify stakeholders with change results) |  |  | Report Confirmation | Report Confirmation

## Legend
Legend / Color Guide
Change Intake node | Steps 0–5: Blue left border
Change Resolution node | Steps 6–13: Green left border
Change Closure node | Steps 14–18: Amber left border
◆ Decision Gate | Diamond: full purple border, decision point
⚠ Failure / Rollback | Red border: failure path
✓ Success | Green: successful completion
External Trigger | Purple: incident/problem process triggers
Service Manager action | Amber border: SM / Other team actions